## Project Timeline
Project Milestones
Date | Milestone | Assigned To | Position | Baseline
2018-02-24 | Bootcamp | Semester1 Week1 | 20 | 0
2018-03-02 | Team Building | Semester1 Week2 | 10 | 0
2018-03-03 | Initial Requirement Analysis | Semester1 Week2 | -5 | 0
2018-03-06 | Preliminary Design | Semester1 Week3 | 25 | 0
2018-03-08 | Design Approval | Semester1 Week3 | -15 | 0
2018-03-14 | Preliminary Front-end prototype | Semester1 Week4 | 15 | 0
2018-03-28 | First Deliverable | Semester1 Week6 | -10 | 0
2018-04-18 | Second Deliverable | Semester1 Week7 | 15 | 0
2018-04-30 | Final prototype | Semester1 Week10 | -15
2018-05-03 | Showcase | Semester1 Week10 | 15

## Sheet1
2018-07-20 | Web Development Finish | Semester2 Week1 | 20
2018-07-27 | Unit Test Finish | Semester2 Week2 | -15
2018-08-03 | Dataset Validation | Semester2 Week3 | 10
2018-08-24 | NLP Model Finish | Semester2 Week6 | 5
2018-08-31 | Unit Test | Semester2 Week7 | -15
2018-09-14 | Document Finish | Semester2 Week9 | 5
2018-09-21 | Project End | Semester2 Week10 | 5